## ReadMe - SIPOC & RACI
SIPOC | = | Suppliers, Inputs, Process, Outputs and Customers
Suppliers | = | Provider of Inputs to the Process
Inputs | = | Define the material, service and/or information that are used by the process to produce the outputs
Process | = | A defined sequence of activities, usually adds value to Inputs to produce Outputs for the Customers. Transforms Input to Output. Verb>Noun Structure 4 to 7 high level steps
Outputs | = | The products, services, and/or information (transformed Inputs) that are valuable to the Customers
Customers | = | The users of the Outputs produced by the Process.
1Purpose: |  | To give people who are unfamiliar with a process a high-level overview
To reacquaint people whose familiarity with a process has faded or become out-of-date due to process changes
To help people in defining a new process
Support the definition, structuring and scoping of complex processes
Identifying possible problems and/or weaknesses in work processes
What the process IS, not what it should be
1Assumptions: |  | Suppliers and customers may be internal or external to the organization that performs the process.
Inputs and outputs may be materials, services, or information.
The focus is on capturing the set of inputs and outputs rather than the individual steps in the process
2Phases: | 1 | Name the Process
| 2 | Map it in 4 to 7 high level steps:
2a First step
2b Last Step
2c In-between steps
| 3 | Identify the outputs of this process.
| 4 | Identify the customers that will receive the outputs of this process.
| 5 | Identify the inputs required for the process to function properly.
| 6 | Identify the suppliers of the inputs that are required by the process.
| 7 | Discuss with project sponsor, Champion and other involved stakeholders for verification.
3RACI |  | There is a distinction between a role and individually identified people: a role is a descriptor of an associated set of tasks; may be performed by many people; and one person can perform many roles.
| R | Responsible (also Recommender): Those who do the work to complete the task. There is at least one role with a participation type of responsible, although others can be delegated to assist in the work required.
| A | Accountable (also Approver or final approving authority): The one ultimately answerable for the correct and thorough completion of the deliverable or task, the one who ensures the prerequisites of the task are met and who delegates the work to those responsible. In other words, an accountable must sign off (approve) work that responsible provides. There must be only one accountable specified for each task or deliverable.
| C | Consulted (sometimes Consultant or counsel): Those whose opinions are sought, typically subject matter experts; and with whom there is two-way communication.
| I | Informed (also Informee): Those who are kept up-to-date on progress, often only on completion of the task or deliverable; and with whom there is just one-way communication
The RACI can be completed by creating a matrix where the rows are at a minimum the process steps from the SIPOC, but could be augmented with more granular steps.
The RACI can be then be filled out in one of two manners: v1) the columns represent R-A-C-I and for each process the role(s)/person(s) is/are identified. Each step must have someone responsible (can be multiple) and accountable (can only be one); v2) the columns represent the various roles, and for each step one indicates if the role is responsible, accountable, consulted and/or informed.
Notes: | 1 | Adapted from https://en.wikipedia.org/wiki/SIPOC
| 2 | Adapted from https://www.isixsigma.com/tools-templates/sipoc-copis/sipoc-diagram/
| 3 | Adapted from https://en.wikipedia.org/wiki/Responsibility_assignment_matrix
150. 0. 0
192.0.0
255.217.217
30.83.87
38. 104. 109
147.180.182
68.35.105
162.145.180
195, 185, 207
201216235
131.158.193
69.99.139
212.223.72
84.130.53

## SIPOC - Classic Digitization
University Libraries Digital Preservation & Access SIPOC Template
High Level Process (Phase 1): | Classic Digitization Project |  |  | Prepared By: | Preservation & Digitization (Preservation & Digitization includes, DigitizationTeam & Conservation Team
Suppliers | Inputs | Process |  | Outputs | Customers
Who provides the inputs? | What inputs are provides? | What are the high level process steps? |  | What outputs are provided? | Who recieves a deliverable from the process?
SIPOC (Phase 6) | SIPOC (Phase 5) | SIPOC (Phase 2) |  | SIPOC (Phase 3) | SIPOC (Phase 4)
Project Owner (Curator, collection manager etc...) | Project Proposal Form | First Step | Receive & Review Project Proposal | Proposal Review (after consultation with all partners) | Conservation & Digitization Project Partners (IT, Metadata, Cataloging etc ...)
Conservation & Digitization Project Partners | Recommendations | Step 2 | Approve the Project | Decision | Project Owner & Partners
Project Owner Project Partners | Materials with Inventory & Metadata | Step 3 | Receive Materials & Inventory | Conservation & Digitization Work plan | Project Owner Partners Preservation & Digitization
Conservation & Digitization | Conservation needs | Step 4 | Complete Conservation Treatment | Conservation Documentation & Treatment | Digitization Team
Digitization Team | Digitization work | Step 5 | Digitize & Deliver Digital Objects | Digital surrogates & potential items to Conservation Treatment | Project Partners Conservation Team
Conservation & Digitization | Conservation work and final documentation | Step 6 | Complete Conservation Treatment post digitization if needed and return physical items | Signed inventory forms | Project Owner
Conservation & Digitization | Project Data | Last Step | Write project report | Project Final report - basic documentation of project- decisions, processes, success & lessons learned | Project Owner Project Partners

## Example - SIPOC
University Libraries Digital Preservation & Access SIPOC Template
High Level Process (Phase 1): | Archives Digitzation |  |  | Prepared By: | Tamar Chute, Carly Dearborn, Michelle Drobik, Kevlin Haire, Laura Kissel & Halle Mares
Suppliers | Inputs | Process |  | Outputs | Customers
Who provides the inputs? | What inputs are provides? | What are the high level process steps? |  | What outputs are provided? | Who recieves a deliverable from the process?
SIPOC (Phase 6) | SIPOC (Phase 5) | SIPOC (Phase 2) |  | SIPOC (Phase 3) | SIPOC (Phase 4)
Patron Archives staff External funding (grant or donor) | Patron request Project proposal | First Step | Request for digitization | content identification/location information | Archives staff (paging)
Archives staff | Original materials | Step 2 | Assess the original materials | Conditon analysis | Archives staff Conservation staff Digitization staff Patron
Archives staff Digitization staff Conservation staff Patron | Decision to digitize | Step 3 | Prepping for digitization | Metadata documentation (spreadsheet/database) patron invoice/payments (list of materials to be digitized) send to off-site vendor | Archives staff Digitization staff Vendor Patron
Archives staff Digitization staff Vendor Patron | Original material Patron payment | Step 4 | Digitize materials | Digital files Digitization metadata | Archives staff
Archives staff Digitization staff | Digitized materials | Step 5 | Quality Control & Evaluation | Approved quality of product | Archives staff Digitization staff Vendor
Archives staff Digitization staff | Completed digital files and metadata | Step 6 | Delivery of digitized content | Access copy Preservation copy | Patron Archives staff Library Staff
Archives staff Library Staff | Original material Digitized material | Last Step | Storage of materials | Access copy Preservation copy Stored Original Materials | Researchers (internal & external) Access & Preservation platform(s) Stacks

## RACI v1
SIPOC Process Step1 | Responsible | Accountable | Consulted | Informed
Receive Project Proposal | Pres Dig Project Coord- Sarah Project Owner | Pres Dig Project Coord- Sarah | Digitization- Amy Conservation - Marcela Partners - ADA - Cate Partners - Metadata- Anna Partners - Copyright- Maria Partners-DigPres-Dan Partners-PRS-Johanna Partners-IT | Pres Dig Strategist- Miriam
Approve the Project | Pres Dig Strategist- Miriam | Pres Dig Strategist- Miriam | Digitization- Amy Conservation - Marcela Partners - ADA - Cate Partners - Metadata- Anna Partners - Copyright- Maria Partners-DigPres-Dan Partners-PRS-Johanna Partners-IT | Pres Dig Project Coord- Sarah Project Owner
Receive Materials & Inventory | Pres Dig Project Coord- Sarah Digitization- Amy Conservation - Marcela Project Owner | Pres Dig Project Coord- Sarah | Partners - ADA - Cate Partners - Metadata- Anna | Pres Dig Strategist- Miriam Partners - Copyright- Maria Partners-DigPres-Dan Partners-PRS-Johanna Partners-IT
Complete Conservation Treatment | Conservation - Marcela | Conservation - Marcela | Project Owner | Pres Dig Project Coord- Sarah Pres Dig Strategist- Miriam Digitization- Amy Partners - ADA - Cate Partners - Metadata- Anna Partners - Copyright- Maria Partners-DigPres-Dan Partners-PRS-Johanna Partners-IT
Digitize & Deliver Digital Objects | Digitization- Amy | Digitization- Amy | Partners - ADA - Cate Partners - Metadata- Anna Partners - DigPres- Dan Partners - PRS- Johanna Partners - IT Conservation - Marcela | Pres Dig Project Coord- Sarah Pres Dig Strategist- Miriam Project Owner Partners-Copyright-Maria
Complete Conservation Treatment post digitization if needed and return physical items | Digitization- Amy Conservation - Marcela Project Owner | Conservation - Marcela | Project owner | Pres Dig Project Coord- Sarah Pres Dig Strategist- Miriam Partners - ADA - Cate Partners - Metadata- Anna Partners - Copyright- Maria Partners-DigPres-Dan Partners-PRS-Johanna Partners-IT
Write project report | Pres Dig Project Coord- Sarah Pres Dig Strategist- Miriam Digitization- Amy Conservation - Marcela | Pres Dig Strategist- Miriam | Project Owner Partners - ADA - Cate Partners - Metadata- Anna Partners - Copyright- Maria Partners-DigPres-Dan Partners-PRS-Johanna Partners-IT | Project Owner Partners - ADA - Cate Partners - Metadata- Anna Partners - Copyright- Maria Partners-DigPres-Dan Partners-PRS-Johanna Partners-IT
1At a minimum, identify the process steps from the SIPOC; but this can be augmented with more granular steps.

## RACI v2
SIPOC Process Step | Internal |  |  |  | External
| Pres Dig Project Coord- Sarah | Pres Dig Strategist- Miriam | Digitization- Amy | Conservation - Marcela | Project Owner1 | Partners - ADA - Cate | Partners - Metadata- Anna | Partners - Copyright- Maria | Partners - DigPres- Dan | Partners - PRS- Johanna | Partners - IT
Receive & Review Project Proposal | Accountable Responsible | Informed | Consulted | Consulted | Responsible | Consulted | Consulted | Consulted | Consulted | Consulted | Consulted
Approve the Project | Informed | Accountable Responsible | Consulted | Consulted | Informed | Consulted | Consulted | Consulted | Consulted | Consulted | Consulted
Receive Materials & Inventory | Accountable Responsible | Informed | Responsible | Responsible | Responsible | Consulted | Consulted | Informed | Informed | Informed | Informed
Complete Conservation Treatment | Informed | Informed | Informed | Accountable Responsible | Consulted | Informed | Informed | Informed | Informed | Informed | Informed
Digitize & Deliver Digital Objects | Informed | Informed | Accountable Responsible | Consulted | Informed | Consulted | Consulted | Informed | Consulted | Consulted | Consulted
Complete Conservation Treatment post digitization if needed and return physical items | Informed | Informed | Responsible | Accountable Responsible | Responsible | Informed | Informed | Informed | Informed | Informed | Informed
Write project report | Responsible | Accountable Responsible | Responsible | Responsible | Consulted | Consulted | Consulted | Consulted | Consulted | Consulted | Consulted
Identify who is: - Responsible - Accountable - Consulted - Informed
1whomever owns the project; potentially curatorial staff or PRS if managing work for other department

## Example - RACI
SIPOC Process Step1 | Responsible | Accountable | Consulted | Informed
Request for digitization: Patron Request | Archives staff | Collection Head2 |  | Archives paging staff
Request for digitization: Project Proposal | Archives staff | Collection Head | Preservation & Digitization | Archives paging staff
Assess the original materials | Archives staff | Collection Head | Preservation & Digitization | Archives staff Patron
Prepping for digitization | Archives staff | Collection Head | Preservation & Digitization
Prepping for digitization: Vendor | Preservation & Digitization | Digitzation Unit Head | Archives Staff | Vendor
Digitize materials: Internal | Archives staff | Collection Head | Preservation & Digitization
Digitize materials: Preservation & Digitzation | Preservation & Digitization | Digitzation Unit Head | Archives Staff
Digitize materials: Vendor | Vendor | Preservation & Digitization | Archives Staff
Quality Control & Evaluation: Internal | Archives staff | Collection Head
Quality Control & Evaluation: Preservation & Digitzation or Vendor | Preservation & Digitization | Digitzation Unit Head |  | Archives staff
Delivery of digitized content | Archives staff | Collection Head |  | Patron
Storage of materials | Archives staff | Collection Head | Digital Preservation Publishing & Repository Services | Archives paging staff
SIPOC Process Step1 | Internal |  |  | External2
| Archives Staff | Collection Head | Archives Paging Staff | Preservation & Digitization | Digitization Unit Head | Vendor | Digital Preservation | Publishing and Respository Services | Patron
Request for digitization: Patron Request | Responsible | Accountable | Informed
Request for digitization: Project Proposal | Responsible | Accountable | Informed | Consulted
Assess the original materials | Responsible Informed | Accountable |  | Consulted |  |  |  |  | Informed
Prepping for digitization | Responsible | Accountable |  | Consulted
Prepping for digitization: Vendor | Consulted |  |  | Responsible | Accountable | Informed
Digitize materials: Internal | Responsible | Accountable |  | Consulted
Digitize materials: Preservation & Digitzation | Consulted |  |  | Responsible | Accountable
Digitize materials: Vendor | Consulted |  |  | Accountable |  | Responsible
Quality Control & Evaluation: Internal | Responsible | Accountable
Quality Control & Evaluation: Preservation & Digitzation or Vendor | Informed |  |  | Responsible | Accountable
Delivery of digitized content | Responsible | Accountable | [6 empty] | Informed
Storage of materials | Responsible | Accountable | Informed |  |  |  | Consulted | Consulted

## ReadMe - Brainwriting
Brainwriting Template v1.2 2020.09.09
This is meant to detail all the micro-steps of a Process Step within the SIPOC encompass. This is an opportunity to identify all the detail encompassed within a SIPOC Process Step and to articulate dependencies.
Further, this provides the opportunity to detail separate channels within a more encompassing workflow.
For Example: | The "Archives Digitization" Workflow can be subdivided into at least two channels:
Channel 01: Patron Digitization Requests (can be further divided into sub-channels based upon format or size)
Channel 01-01: Patron Digitization Requests - Photo(s)
Channel 02: Project Digitization
The "Born Digital Accessioning" Workflow can be subdivided at least two and maybe eventually three channels:
Channel 01: University Records
Channel 02: Congressional Records
Channel 03: Polar Records
Therefore this Brainwriting part of this template has been constructed with a minimum of three tabs for channels or sub-channels.
Additional Tabs/Channels can be added as necessary; HOWEVER, keep in mind not all workflows will need more than one channel.
Instructions:
1. Identify the appropriate workflow
2. Identify the appropriate Channel(s)/Sub-channel(s) if necessary
3. Fill in all appropriate steps from your Unit's SIPOC. For Brainwriting, the Steps are represented as Columns as opposed to Rows. If there are less than seven steps, delete the appropriate columns.
4. Fill out step details in rows below each Step that are necessary to complete that Process Step.
5. When necessary, create notes or identify dependencies for the Process Step Details. Dpendencies are the relationship between conditions, events, or tasks such that one cannot begin or be-completed until one or more other conditions, events, or tasks have occurred, begun, or completed.
Below are two partially completed examples. These are not meant to represent a fully complete brainwriting exercise.
Example #1:
Workflow: | Archives Digitization
Channel: | 01-01 Patron Request: Photo(s)
First Step |  | Step 2 |  | Step 3 |  | Step 4 |  | Step 5 |  | Step 6 |  | Last Step
Request for digitization | Notes or Dependencies | Assess the original materials | Notes or Dependencies | Prepping for digitization | Notes or Dependencies | Digitize materials | Notes or Dependencies | Quality Control & Evaluation | Notes or Dependencies | Delivery of digitized content | Notes or Dependencies | Storage of materials | Notes or Dependencies
Patron request | May be via email, phone or in person | Determine if materials have already been digitized or not |  | Add order into Photos Order database |  | Internal: Scan to requested file format |  | Permanent Archives staff review scans |  | Patron sent scans typically via Box link |  | Preservation & Digitization returns materials to Archives
Identify patron use |  | Determine if materials can be digitized |  |  |  | Preservation & Digitization scan/image to TIFF and files transferred to K-Drive | [5 empty] | Vendor returns materials to Archives
|  | Evaluate condition | [9 empty] | Materials returned to stacks
|  | Evaluate rights |  |  |  | Vendor scans typically transferred via external media, that is then transferred to the K-Drive.
Determine tools to be used
|  | Determine if it can be done in house | Need to consult w/Preservation & Digitization
|  | If it needs to be outsourced determine cost to patron | Need to consult w/Preservation & Digitization
Charge patron for the digitization
Example #2:
Workflow: | Born Digital Accessioning
Channel: | 01 University Records
First Step |  | Step 2 |  | Step 3 |  | Step 4 |  | Last Step
Request to transfer electronic records to Archives | Notes or Dependencies | Appraise material | Notes or Dependencies | Transfer material | Notes or Dependencies | Accession material | Notes or Dependencies | Store material | Notes or Dependencies
Ohio State Records Retention Schedule requires transfer to Archives | Consolation with RM and or Asst Univ Archivist | Donor interview (?) questions about history of computer use, types of files they create, types of files they save, tasks they use computer for ... try to figure out what you might see in a digital donation |  | Follow-up with the Dept to actually transfer the records |  | Asst Univ Archivist creates accession record |  | transfer files from temporary storage to DC or other platform(s) tbd
donor indicates they have digital files as part of their collection |  | Communicate to donor the types of records we do and don't want |  | Coordinate w/Digital Preservation Librarian the means of transfer
Archives asks for size estimate and general description of materials |  | Request transferring Dept to create files manifest |  | transfer files | Depending on size, security/privacy, immediacy may be to Box, DarkArchive or K-Drive
Small donations can be sent via email |  | transferring Dept creates manifest | May need to consult w/Digital Preservation Librarian
Large donations consult w/Digital Preservation Librarian | Digital Preservation Librarian may need to consult w/IT-Infrastructure | Archives reviews manifest | May need to consult w/Digital Preservation Librarian
If records are not to be transferred to Archives, remind Dept to complete CRD and destroy the records

## BW Channel 01
Workflow: | Classic Digitization Project
Channel:
First Step |  | Step 2 |  | Step 3 |  | Step 4 |  | Step 5 |  | Step 6 |  | Last Step
Receive & Review Project Proposal | Notes or Dependencies | Approve the Project | Notes or Dependencies | Receive Materials & Inventory | Notes or Dependencies | Complete Conservation Treatment | Notes or Dependencies | Digitize & Deliver Digital Objects | Notes or Dependencies | Complete Conservation Treatment post digitization if needed and return physical items | Notes or Dependencies | Write project report | Notes or Dependencies
Coordinator intakes proposal form | Project owner submitted all needed information | Compile results of project partner review | Complete input from project partners | Transport of materials to LTC | Coordination of transport (MS Teams) and student/transport staff availability/need a van | Conservation item assessment | Conservator and Digitization heads have availability to meet | Digitization testing and setup(s) | Different types, condition and sizes of materials, may require multiple setups, availability of digitization equipment | Digitization sends items to conservation for further treatment or re-housing | Digitization flagging items that need further treatment | Project closure checklist | all steps of project completed and deliverables fulfilled
DigiPres leads review form | Have PM tools | Evaluate feasability | Recommendations from project partners | Review of inventory list | Need list provided by project owner-must be an electronic document | Treatment proposal | Conservator and Digitization heads have availability to meet | Assess results of testing and determine specs and process steps | Availability of Digi lead to sign off on specs and process | completion of treatments or re-housing | conservation team availability | Post project evaluation survey | coordinator sends (email) survey out to all stakeholders
Physical condition assessment of materials | Minimal processing of materials (finding aid,etc.) and access to physical materials | Decide to move forward, defer, or decline project | Strategist makes decision | Assignation of location in PresDig of the materials while they await work | Secure space or storage in conservation lab | Conservation team performs treatment | availability of conservation staff time and materials | Digitize materials | Available staff, equipment, software | Document treatments in MARC record | permission to edit Sierra | Formal project closure meeting with all stakeholders | availability of all stakeholders to meet, ability to honestly discuss what went right and what needs improvement
Consult with project owner | Finding meeting availability with PresDig | Record why project is declined or defered | Coordinator compiles a report | Consult with project owner for any missing material or information | Use PM tool ME Teams | Completed treatment | Inform project owners and stakeholders that items ready for digitization | Post-process | Available staff, equipment, software | Items returned to coordinator for return | coordinator tracking inventory | Add new information to Digi best practices | if any new practices were though of or came up during project
Reach out to metadata, copyright, digital preservation, and IT for review | Use of PM tool (MSTeams) to keep track of progress and communicate review process | Communicate with project owner | Continued communication throughout process so project owner knows why the decision was made and any conditions needed to allow project to move forward |  |  |  |  | Conversion of images to output format | Available staff, equipment, and software. Clear, agreed-upon policies within the Libraries |  |  | Information gathered for all of the above complied into final project report by coordinator | the quality of information gathered
[8 empty] | Quality check of images | Available staff, equipment, software
[8 empty] | Uploading of images to appropriate working space | Available disc space on network drive. Clear indication of where images should be uploaded
[8 empty] | Communicate with Metadata that images are ready on network drive | PM tools, ability of MI to process images for ingest

## BW Channel 02
Workflow:
Channel:
First Step |  | Step 2 |  | Step 3 |  | Step 4 |  | Step 5 |  | Step 6 |  | Last Step
| Notes or Dependencies |  | Notes or Dependencies |  | Notes or Dependencies |  | Notes or Dependencies |  | Notes or Dependencies |  | Notes or Dependencies |  | Notes or Dependencies

## BW Channel 03
Workflow:
Channel:
First Step |  | Step 2 |  | Step 3 |  | Step 4 |  | Step 5 |  | Step 6 |  | Last Step
| Notes or Dependencies |  | Notes or Dependencies |  | Notes or Dependencies |  | Notes or Dependencies |  | Notes or Dependencies |  | Notes or Dependencies |  | Notes or Dependencies

## Resources
Lean Six Sigma Technique Tips - SIPOC | Pyzdek Institute | https://www.youtube.com/watch?v=AlN7eNOBPzg | 7 minutes
How to complete the SIPOC Diagram | Six Sigma Development Solutions Inc. | https://youtu.be/x8_I19PJBY8 | 1 minute
SIPOC | Wikipedia | https://en.wikipedia.org/wiki/SIPOC
SIPOC | LeanOhio | https://www.youtube.com/watch?v=_2_Ijfg4EVk | 4 minutes
SIPOC Diagram explained (with example) | Bzhwen A Kadir | https://www.youtube.com/watch?v=j9oWnnbtkOo | 7 minutes