## ReadMe - SIPOC & RACI
SIPOC | = | Suppliers, Inputs, Process, Outputs and Customers
Suppliers | = | Provider of Inputs to the Process
Inputs | = | Define the material, service and/or information that are used by the process to produce the outputs
Process | = | A defined sequence of activities, usually adds value to Inputs to produce Outputs for the Customers. Transforms Input to Output. Verb>Noun Structure 4 to 7 high level steps
Outputs | = | The products, services, and/or information (transformed Inputs) that are valuable to the Customers
Customers | = | The users of the Outputs produced by the Process.
1Purpose: |  | To give people who are unfamiliar with a process a high-level overview
To reacquaint people whose familiarity with a process has faded or become out-of-date due to process changes
To help people in defining a new process
Support the definition, structuring and scoping of complex processes
Identifying possible problems and/or weaknesses in work processes
What the process IS, not what it should be
1Assumptions: |  | Suppliers and customers may be internal or external to the organization that performs the process.
Inputs and outputs may be materials, services, or information.
The focus is on capturing the set of inputs and outputs rather than the individual steps in the process
2Phases: | 1 | Name the Process
| 2 | Map it in 4 to 7 high level steps:
2a First step
2b Last Step
2c In-between steps
| 3 | Identify the outputs of this process.
| 4 | Identify the customers that will receive the outputs of this process.
| 5 | Identify the inputs required for the process to function properly.
| 6 | Identify the suppliers of the inputs that are required by the process.
| 7 | Discuss with project sponsor, Champion and other involved stakeholders for verification.
3RACI |  | There is a distinction between a role and individually identified people: a role is a descriptor of an associated set of tasks; may be performed by many people; and one person can perform many roles.
| R | Responsible (also Recommender): Those who do the work to complete the task. There is at least one role with a participation type of responsible, although others can be delegated to assist in the work required.
| A | Accountable (also Approver or final approving authority): The one ultimately answerable for the correct and thorough completion of the deliverable or task, the one who ensures the prerequisites of the task are met and who delegates the work to those responsible. In other words, an accountable must sign off (approve) work that responsible provides. There must be only one accountable specified for each task or deliverable.
| C | Consulted (sometimes Consultant or counsel): Those whose opinions are sought, typically subject matter experts; and with whom there is two-way communication.
| I | Informed (also Informee): Those who are kept up-to-date on progress, often only on completion of the task or deliverable; and with whom there is just one-way communication
The RACI can be completed by creating a matrix where the rows are at a minimum the process steps from the SIPOC, but could be augmented with more granular steps.
The RACI can be then be filled out in one of two manners: v1) the columns represent R-A-C-I and for each process the role(s)/person(s) is/are identified. Each step must have someone responsible (can be multiple) and accountable (can only be one); v2) the columns represent the various roles, and for each step one indicates if the role is responsible, accountable, consulted and/or informed.
Notes: | 1 | Adapted from https://en.wikipedia.org/wiki/SIPOC
| 2 | Adapted from https://www.isixsigma.com/tools-templates/sipoc-copis/sipoc-diagram/
| 3 | Adapted from https://en.wikipedia.org/wiki/Responsibility_assignment_matrix
150. 0. 0
192.0.0
255.217.217
30.83.87
38. 104. 109
147.180.182
68.35.105
162.145.180
195, 185, 207
201216235
131.158.193
69.99.139
212.223.72
84.130.53

## Example - SIPOC
University Libraries Digital Preservation & Access SIPOC Template
High Level Process (Phase 1): | Archives Digitzation |  |  | Prepared By: | Tamar Chute, Carly Dearborn, Michelle Drobik, Kevlin Haire, Laura Kissel & Halle Mares
Suppliers | Inputs | Process |  | Outputs | Customers
Who provides the inputs? | What inputs are provides? | What are the high level process steps? |  | What outputs are provided? | Who recieves a deliverable from the process?
SIPOC (Phase 6) | SIPOC (Phase 5) | SIPOC (Phase 2) |  | SIPOC (Phase 3) | SIPOC (Phase 4)
Patron Archives staff External funding (grant or donor) | Patron request Project proposal | First Step | Request for digitization | content identification/location information | Archives staff (paging)
Archives staff | Original materials | Step 2 | Assess the original materials | Conditon analysis | Archives staff Conservation staff Digitization staff Patron
Archives staff Digitization staff Conservation staff Patron | Decision to digitize | Step 3 | Prepping for digitization | Metadata documentation (spreadsheet/database) patron invoice/payments (list of materials to be digitized) send to off-site vendor | Archives staff Digitization staff Vendor Patron
Archives staff Digitization staff Vendor Patron | Original material Patron payment | Step 4 | Digitize materials | Digital files Digitization metadata | Archives staff
Archives staff Digitization staff | Digitized materials | Step 5 | Quality Control & Evaluation | Approved quality of product | Archives staff Digitization staff Vendor
Archives staff Digitization staff | Completed digital files and metadata | Step 6 | Delivery of digitized content | Access copy Preservation copy | Patron Archives staff Library Staff
Archives staff Library Staff | Original material Digitized material | Last Step | Storage of materials | Access copy Preservation copy Stored Original Materials | Researchers (internal & external) Access & Preservation platform(s) Stacks

## SIPOC - Digitization
University Libraries Digital Preservation & Access SIPOC Template
High Level Process (Phase 1): | Digitization work |  |  | Prepared By: | Preservation & Digitization (Preservation & Digitization includes, DigitizationTeam & Conservation Team
Suppliers | Inputs | Process |  | Outputs | Customers
Who provides the inputs? | What inputs are provides? | What are the high level process steps? |  | What outputs are provided? | Who recieves a deliverable from the process?
SIPOC (Phase 6) | SIPOC (Phase 5) | SIPOC (Phase 2) |  | SIPOC (Phase 3) | SIPOC (Phase 4)
Conservation Team Digitization Team | Conservation & Digitization Work Plan | First Step | Create a workflow in Project Management Tool | Plan with a schedule | Project Owner (Curator, collection manager etc...) Project Partners (IT, Metadata, Cataloging etc ...) Conservation Team Digitization Team
Digitization Team Vendor | Preliminary Sample photographs | Step 2 | Determining if the imaging fulfills the project objectives | Confirmation of decision from Project Owner | Project Owner
Digitization Team | Analog objects that need treatment | Step 3 | Conservation Treatment and Documentation | Analog objects that have been treated | Digitization Team
Conservation Team | Analog materials ready for digitization | Step 4 | Digital capture | Digital objects | Digitization Team Vendor
Digitization Team Vendor | Raw images | Step 5 | Post processing, conversion and QC | Processed digital objects | Digitization Team Vendor
Dgiitization Team | Processed digital objects | Step 6 | Deliver/upload digitial objects | Staged digital objects | Metadata Initiatives Librarian Project Owner IT
Conservation Team Digitization Team | Analog objects | Last Step | Inventory, pack and return analog materials | Returned materials | Project Owner

## RACI v1
SIPOC Process Step1 | Responsible | Accountable | Consulted | Informed
Create a workflow in Project Management Tool | Digitization | Conservation | Partners | Project Owner
Determining if the imaging fulfills the project objectives | Digitization | Digitization | Project Owner | Conservation Project Owner Partners
Conservation Treatment and Documentation | Digitization Conservation | Conservation | Project Owner Partners
Digital capture | Digitization | Digitization | Digitization | Conservation Project Owner Partners
Post processing, conversion and QC | Digitization | Digitization | Partners | Conservation Project Owner
Deliver/upload digitial objects | Digitization | Digitization | Project Owner Partners | Conservation
Inventory, pack and return analog materials | Digitization Conservation Project Owner | Digitization | Project Owner | Partners
1At a minimum, identify the process steps from the SIPOC; but this can be augmented with more granular steps.

## RACI v2
SIPOC Process Step1 | Internal |  |  |  | External2
| PresDig Project Coord - Sarah | Digitization Program Manager- Amy | Head of Conservation - Marcela | PresDig Strategist - Miriam | Project Owner | Partners
Create a workflow in Project Management Tool | Responsible Accountable | Responsible | Responsible | Informed | Informed | Consulted
Determining if the imaging fulfills the project objectives | Informed | Responsible Accountable | Informed | Informed | Consulted | Informed
Conservation Treatment and Documentation | Informed | Informed | Responsible Accountable | Informed | Consulted | Consulted
Digital capture | Informed | Responsible Accountable | Informed | Informed | Informed | Informed
Post processing, conversion and QC | Informed | Responsible Accountable | Informed | Informed | Informed | Consulted
Deliver/upload digitial objects | Informed | Responsible Accountable | Informed | Informed | Consulted | Consulted
Inventory, pack and return analog materials | Responsible | Accountable | Consulted | Informed | Responsible | Informed
1At a minimum, identify the process steps from the SIPOC; but this can be augmented with more granular steps.
2"External" to the unit creating the SIPOC (e.g. Metadata Initiatives is "external" to Preservation & Digitization)
3While the template identifies 8 roles, this is neither a minimum nor a maximum, it all depends upon your workflow and processes. Name the roles (and/or individuals) Identify who is: - Responsible - Accountable - Consulted - Informed

## Example - RACI
SIPOC Process Step1 | Responsible | Accountable | Consulted | Informed
Request for digitization: Patron Request | Archives staff | Collection Head2 |  | Archives paging staff
Request for digitization: Project Proposal | Archives staff | Collection Head | Preservation & Digitization | Archives paging staff
Assess the original materials | Archives staff | Collection Head | Preservation & Digitization | Archives staff Patron
Prepping for digitization | Archives staff | Collection Head | Preservation & Digitization
Prepping for digitization: Vendor | Preservation & Digitization | Digitzation Unit Head | Archives Staff | Vendor
Digitize materials: Internal | Archives staff | Collection Head | Preservation & Digitization
Digitize materials: Preservation & Digitzation | Preservation & Digitization | Digitzation Unit Head | Archives Staff
Digitize materials: Vendor | Vendor | Preservation & Digitization | Archives Staff
Quality Control & Evaluation: Internal | Archives staff | Collection Head
Quality Control & Evaluation: Preservation & Digitzation or Vendor | Preservation & Digitization | Digitzation Unit Head |  | Archives staff
Delivery of digitized content | Archives staff | Collection Head |  | Patron
Storage of materials | Archives staff | Collection Head | Digital Preservation Publishing & Repository Services | Archives paging staff
SIPOC Process Step1 | Internal |  |  | External2
| Archives Staff | Collection Head | Archives Paging Staff | Preservation & Digitization | Digitization Unit Head | Vendor | Digital Preservation | Publishing and Respository Services | Patron
Request for digitization: Patron Request | Responsible | Accountable | Informed
Request for digitization: Project Proposal | Responsible | Accountable | Informed | Consulted
Assess the original materials | Responsible Informed | Accountable |  | Consulted |  |  |  |  | Informed
Prepping for digitization | Responsible | Accountable |  | Consulted
Prepping for digitization: Vendor | Consulted |  |  | Responsible | Accountable | Informed
Digitize materials: Internal | Responsible | Accountable |  | Consulted
Digitize materials: Preservation & Digitzation | Consulted |  |  | Responsible | Accountable
Digitize materials: Vendor | Consulted |  |  | Accountable |  | Responsible
Quality Control & Evaluation: Internal | Responsible | Accountable
Quality Control & Evaluation: Preservation & Digitzation or Vendor | Informed |  |  | Responsible | Accountable
Delivery of digitized content | Responsible | Accountable | [6 empty] | Informed
Storage of materials | Responsible | Accountable | Informed |  |  |  | Consulted | Consulted

## ReadMe - Brainwriting
Brainwriting Template v1.2 2020.09.09
This is meant to detail all the micro-steps of a Process Step within the SIPOC encompass. This is an opportunity to identify all the detail encompassed within a SIPOC Process Step and to articulate dependencies.
Further, this provides the opportunity to detail separate channels within a more encompassing workflow.
For Example: | The "Archives Digitization" Workflow can be subdivided into at least two channels:
Channel 01: Patron Digitization Requests (can be further divided into sub-channels based upon format or size)
Channel 01-01: Patron Digitization Requests - Photo(s)
Channel 02: Project Digitization
The "Born Digital Accessioning" Workflow can be subdivided at least two and maybe eventually three channels:
Channel 01: University Records
Channel 02: Congressional Records
Channel 03: Polar Records
Therefore this Brainwriting part of this template has been constructed with a minimum of three tabs for channels or sub-channels.
Additional Tabs/Channels can be added as necessary; HOWEVER, keep in mind not all workflows will need more than one channel.
Instructions:
1. Identify the appropriate workflow
2. Identify the appropriate Channel(s)/Sub-channel(s) if necessary
3. Fill in all appropriate steps from your Unit's SIPOC. For Brainwriting, the Steps are represented as Columns as opposed to Rows. If there are less than seven steps, delete the appropriate columns.
4. Fill out step details in rows below each Step that are necessary to complete that Process Step.
5. When necessary, create notes or identify dependencies for the Process Step Details. Dpendencies are the relationship between conditions, events, or tasks such that one cannot begin or be-completed until one or more other conditions, events, or tasks have occurred, begun, or completed.
Below are two partially completed examples. These are not meant to represent a fully complete brainwriting exercise.
Example #1:
Workflow: | Archives Digitization
Channel: | 01-01 Patron Request: Photo(s)
First Step |  | Step 2 |  | Step 3 |  | Step 4 |  | Step 5 |  | Step 6 |  | Last Step
Request for digitization | Notes or Dependencies | Assess the original materials | Notes or Dependencies | Prepping for digitization | Notes or Dependencies | Digitize materials | Notes or Dependencies | Quality Control & Evaluation | Notes or Dependencies | Delivery of digitized content | Notes or Dependencies | Storage of materials | Notes or Dependencies
Patron request | May be via email, phone or in person | Determine if materials have already been digitized or not |  | Add order into Photos Order database |  | Internal: Scan to requested file format |  | Permanent Archives staff review scans |  | Patron sent scans typically via Box link |  | Preservation & Digitization returns materials to Archives
Identify patron use |  | Determine if materials can be digitized |  |  |  | Preservation & Digitization scan/image to TIFF and files transferred to K-Drive | [5 empty] | Vendor returns materials to Archives
|  | Evaluate condition | [9 empty] | Materials returned to stacks
|  | Evaluate rights |  |  |  | Vendor scans typically transferred via external media, that is then transferred to the K-Drive.
Determine tools to be used
|  | Determine if it can be done in house | Need to consult w/Preservation & Digitization
|  | If it needs to be outsourced determine cost to patron | Need to consult w/Preservation & Digitization
Charge patron for the digitization
Example #2:
Workflow: | Born Digital Accessioning
Channel: | 01 University Records
First Step |  | Step 2 |  | Step 3 |  | Step 4 |  | Last Step
Request to transfer electronic records to Archives | Notes or Dependencies | Appraise material | Notes or Dependencies | Transfer material | Notes or Dependencies | Accession material | Notes or Dependencies | Store material | Notes or Dependencies
Ohio State Records Retention Schedule requires transfer to Archives | Consolation with RM and or Asst Univ Archivist | Donor interview (?) questions about history of computer use, types of files they create, types of files they save, tasks they use computer for ... try to figure out what you might see in a digital donation |  | Follow-up with the Dept to actually transfer the records |  | Asst Univ Archivist creates accession record |  | transfer files from temporary storage to DC or other platform(s) tbd
donor indicates they have digital files as part of their collection |  | Communicate to donor the types of records we do and don't want |  | Coordinate w/Digital Preservation Librarian the means of transfer
Archives asks for size estimate and general description of materials |  | Request transferring Dept to create files manifest |  | transfer files | Depending on size, security/privacy, immediacy may be to Box, DarkArchive or K-Drive
Small donations can be sent via email |  | transferring Dept creates manifest | May need to consult w/Digital Preservation Librarian
Large donations consult w/Digital Preservation Librarian | Digital Preservation Librarian may need to consult w/IT-Infrastructure | Archives reviews manifest | May need to consult w/Digital Preservation Librarian
If records are not to be transferred to Archives, remind Dept to complete CRD and destroy the records

## BW Channel 01
Workflow: | Digitization
Channel:
First Step |  | Step 2 |  | Step 3 |  | Step 4 |  | Step 5 |  | Step 6 |  | Last Step
Create a workflow in Project Management Tool | Notes or Dependencies | Determining if the imaging fulfills the project objectives | Notes or Dependencies | Conservation Treatment and Documentation | Notes or Dependencies | Digital capture | Notes or Dependencies | Post processing, conversion and QC | Notes or Dependencies | Deliver/upload digitial objects | Notes or Dependencies | Inventory, pack and return analog materials | Notes or Dependencies
Project manager consults with partners in Pres&Dig about details of the work | Availability of Pres&Dig staff | Digitization program manager (DPM) takes sample photos of collection items | Hardware, software, lighting equipment and workspace |  |  | DPM initiates digitization work or assigns it to appropriate staff and gives them the specifications | Information from project owner; imaging standards | Post processing of images | Project specification; batch processing software | Upload completed images to specified digital storage space | Information from IT and MI about which storage space to use | Check materials to be returned against inventory | Inventory
Project manager creates workflow | Project management software | DPM shares sample photos with project owner | Software and shared space accessible to project partners | Conservation Team Assessment | Conservator and Digitization heads have availability to meet | Sort collection items by size, material type, or other features if this has an impact on digitization setup |  | Quality review of images | Project specification; batch processing software |  |  | Pack materials | Available bins
Project manager assigns tasks to appropriate personnel | Project management software | Project owner approves sample images or requests modifications | Software and shared space accessible to project partners | Treatment proposal | Conservator and Digitization heads have availability to meet | Set up equipment | Projection specifications; appropriate imaging equipment | Conversion of images to output format | Project specification; batch processing software |  |  | Schedule return in Special Collections weekly transport | MS 365 Software
|  | DPM writes specifications for digitization |  | Conservation Team performs treatment | availability of conservation staff time and materials | Capture imaging target and use it to build profile for color, tone, and other quality and standardization features | Appropriate imaging target and profiling software
|  |  |  | Completed treatment | Inform project owners and stakeholders that items ready for digitization | Capture images of collection items | Hardware, software, imaging equipment and workspace

## BW Channel 02
Workflow:
Channel:
First Step |  | Step 2 |  | Step 3 |  | Step 4 |  | Step 5 |  | Step 6 |  | Last Step
| Notes or Dependencies |  | Notes or Dependencies |  | Notes or Dependencies |  | Notes or Dependencies |  | Notes or Dependencies |  | Notes or Dependencies |  | Notes or Dependencies

## BW Channel 03
Workflow:
Channel:
First Step |  | Step 2 |  | Step 3 |  | Step 4 |  | Step 5 |  | Step 6 |  | Last Step
| Notes or Dependencies |  | Notes or Dependencies |  | Notes or Dependencies |  | Notes or Dependencies |  | Notes or Dependencies |  | Notes or Dependencies |  | Notes or Dependencies

## Resources
Lean Six Sigma Technique Tips - SIPOC | Pyzdek Institute | https://www.youtube.com/watch?v=AlN7eNOBPzg | 7 minutes
How to complete the SIPOC Diagram | Six Sigma Development Solutions Inc. | https://youtu.be/x8_I19PJBY8 | 1 minute
SIPOC | Wikipedia | https://en.wikipedia.org/wiki/SIPOC
SIPOC | LeanOhio | https://www.youtube.com/watch?v=_2_Ijfg4EVk | 4 minutes
SIPOC Diagram explained (with example) | Bzhwen A Kadir | https://www.youtube.com/watch?v=j9oWnnbtkOo | 7 minutes