## Template
University Libraries Digital Preservation & Access SIPOC Template
High Level Process (Phase 1): | Archives Digitzation |  |  | Prepared By:
Suppliers | Inputs | Process |  | Outputs | Customers
Who provides the inputs? | What inputs are provides? | What are the high level process steps? |  | What outputs are provided? | Who recieves a deliverable from the process?
SIPOC (Phase 6) | SIPOC (Phase 5) | SIPOC (Phase 2) |  | SIPOC (Phase 3) | SIPOC (Phase 4)
Patron Archives staff External funding (grant or donor) | Patron request Project proposal | First Step | Request for digitization | content identification/location information | Archives staff (paging)
Archives staff | Original materials | Step 2 | Assess the original materials | Conditon analysis | Archives staff Conservation staff Digitization staff Patron
Archives staff Digitization staff Conservation staff Patron | Decision to digitize | Step 3 | Prepping for digitization | Metadata documentation (spreadsheet/database) patron invoice/payments (list of materials to be digitized) send to off-site vendor | Archives staff Digitization staff Vendor Patron
Archives staff Digitization staff Vendor Patron | Original material Patron payment | Step 4 | Digitize materials | Digital files Digitization metadata | Archives staff
Archives staff Digitization staff | Digitized materials | Step 5 | Quality Control & Evaluation | Approved quality of product | Archives staff Digitization staff Vendor
Archives staff Digitization staff | Completed digital files and metadata | Step 6 | Delivery of digitized content | Access copy Preservation copy | Patron Archives staff Library Staff
Archives staff Library Staff | Original material Digitized material | Last Step | Storage of materials | Access copy Preservation copy Stored Original Materials | Researchers (internal & external) Access & Preservation platform(s) Stacks

## RACI v1
SIPOC Process Step1 | Responsible | Accountable | Consulted | Informed
Request for digitization: Patron Request | Archives staff | Collection Head2 |  | Archives paging staff
Request for digitization: Project Proposal | Archives staff | Collection Head | Preservation & Digitization | Archives paging staff
Assess the original materials | Archives staff | Collection Head | Preservation & Digitization | Archives staff Patron
Prepping for digitization | Archives staff | Collection Head | Preservation & Digitization
Prepping for digitization: Vendor | Preservation & Digitization | Digitzation Unit Head | Archives Staff | Vendor
Digitize materials: Internal | Archives staff | Collection Head | Preservation & Digitization
Digitize materials: Preservation & Digitzation | Preservation & Digitization | Digitzation Unit Head | Archives Staff
Digitize materials: Vendor | Vendor | Preservation & Digitization | Archives Staff
Quality Control & Evaluation: Internal | Archives staff | Collection Head
Quality Control & Evaluation: Preservation & Digitzation or Vendor | Preservation & Digitization | Digitzation Unit Head |  | Archives staff
Delivery of digitized content | Archives staff | Collection Head |  | Patron
Storage of materials | Archives staff | Collection Head | Digital Preservation Publishing & Repository Services | Archives paging staff
1At a minimum, identify the process steps from the SIPOC; but this can be augmented with more granular steps.
2Head or University Archives, Byrd Polar Archives or Ohio Congressional Archives

## RACI v2
SIPOC Process Step1 | Internal |  |  | External2
| Archives Staff | Collection Head | Archives Paging Staff | Preservation & Digitization | Digitization Unit Head | Vendor | Digital Preservation | Publishing and Respository Services | Patron
Request for digitization: Patron Request | Responsible | Accountable | Informed
Request for digitization: Project Proposal | Responsible | Accountable | Informed | Consulted
Assess the original materials | Responsible Informed | Accountable |  | Consulted |  |  |  |  | Informed
Prepping for digitization | Responsible | Accountable |  | Consulted
Prepping for digitization: Vendor | Consulted |  |  | Responsible | Accountable | Informed
Digitize materials: Internal | Responsible | Accountable |  | Consulted
Digitize materials: Preservation & Digitzation | Consulted |  |  | Responsible | Accountable
Digitize materials: Vendor | Consulted |  |  | Accountable |  | Responsible
Quality Control & Evaluation: Internal | Responsible | Accountable
Quality Control & Evaluation: Preservation & Digitzation or Vendor | Informed |  |  | Responsible | Accountable
Delivery of digitized content | Responsible | Accountable | [6 empty] | Informed
Storage of materials | Responsible | Accountable | Informed |  |  |  | Consulted | Consulted
1At a minimum, identify the process steps from the SIPOC; but this can be augmented with more granular steps.
2"External" to the unit creating the SIPOC (e.g. Metadata Initiatives is "external" to Preservation & Digitization)
Name the roles (and/or individuals) Identify who is: - Responsible - Accountable - Consulted - Informed

## ReadMe
SIPOC | = | Suppliers, Inputs, Process, Outputs and Customers
Suppliers | = | Provider of Inputs to the Process
Inputs | = | Define the material, service and/or information that are used by the process to produce the outputs
Process | = | A defined sequence of activities, usually adds value to Inputs to produce Outputs for the Customers. Transforms Input to Output. Verb>Noun Structure 4 to 7 high level steps
Outputs | = | The products, services, and/or information (transformed Inputs) that are valuable to the Customers
Customers | = | The users of the Outputs produced by the Process.
1Purpose: |  | To give people who are unfamiliar with a process a high-level overview
To reacquaint people whose familiarity with a process has faded or become out-of-date due to process changes
To help people in defining a new process
Support the definition, structuring and scoping of complex processes
Identifying possible problems and/or weaknesses in work processes
What the process IS, not what it should be
1Assumptions: |  | Suppliers and customers may be internal or external to the organization that performs the process.
Inputs and outputs may be materials, services, or information.
The focus is on capturing the set of inputs and outputs rather than the individual steps in the process
2Phases: | 1 | Name the Process
| 2 | Map it in 4 to 7 high level steps:
2a First step
2b Last Step
2c In-between steps
| 3 | Identify the outputs of this process.
| 4 | Identify the customers that will receive the outputs of this process.
| 5 | Identify the inputs required for the process to function properly.
| 6 | Identify the suppliers of the inputs that are required by the process.
| 7 | Discuss with project sponsor, Champion and other involved stakeholders for verification.
3RACI |  | There is a distinction between a role and individually identified people: a role is a descriptor of an associated set of tasks; may be performed by many people; and one person can perform many roles.
| R | Responsible (also Recommender): Those who do the work to complete the task. There is at least one role with a participation type of responsible, although others can be delegated to assist in the work required.
| A | Accountable (also Approver or final approving authority): The one ultimately answerable for the correct and thorough completion of the deliverable or task, the one who ensures the prerequisites of the task are met and who delegates the work to those responsible. In other words, an accountable must sign off (approve) work that responsible provides. There must be only one accountable specified for each task or deliverable.
| C | Consulted (sometimes Consultant or counsel): Those whose opinions are sought, typically subject matter experts; and with whom there is two-way communication.
| I | Informed (also Informee): Those who are kept up-to-date on progress, often only on completion of the task or deliverable; and with whom there is just one-way communication
The RACI can be completed by creating a matrix where the rows are at a minimum the process steps from the SIPOC, but could be augmented with more granular steps.
The RACI can be then be filled out in one of two manners: v1) the columns represent R-A-C-I and for each process the role(s)/person(s) is/are identified. Each step must have someone responsible (can be multiple) and accountable (can only be one); v2) the columns represent the various roles, and for each step one indicates if the role is responsible, accountable, consulted and/or informed.
Notes: | 1 | Adapted from https://en.wikipedia.org/wiki/SIPOC
| 2 | Adapted from https://www.isixsigma.com/tools-templates/sipoc-copis/sipoc-diagram/
| 3 | Adapted from https://en.wikipedia.org/wiki/Responsibility_assignment_matrix

## Example - SIPOC
University Libraries Digital Preservation & Access SIPOC Template
High Level Process (Phase 1): | Restaurant Visit |  |  | Prepared By: | General Manager, Head Waitperson, & Head Chef
Suppliers | Inputs | Process |  | Outputs | Customers
Who provides the inputs? | What inputs are provides? | What are the high level process steps? |  | What outputs are provided? | Who recieves a deliverable from the process?
SIPOC (Phase 6) | SIPOC (Phase 5) | SIPOC (Phase 2) |  | SIPOC (Phase 3) | SIPOC (Phase 4)
Maître d' | Table request | First Step | Assign table | Occupied table | Restaurant guest
Restaurant guest | Verbal order | Step 2 | Order food | Written order | Wait staff Cooking staff
Cooking staff | Various food products | Step 3 | Prepare food | Prepared meal | Wait staff
Wait staff | Prepared food | Step 4 | Serve food | Delivered meal | Restaurant guest
Restaurant guest | Eating | Step 5 | Eat food | Table to be cleared | Bussing staff
Wait staff | Meal invoice | Step 6 | Pay bill | Money transfer Receipt | Restaurant guest Cashier
Bussing Staff | Reset table | Last Step | Clean table | Available table | Maître d'

## Example - RACI
RACI v1
SIPOC Process Step | Responsible | Accountable | Consulted | Informed
Assign table | Host | Manager | Wait Staff | Patron
Order food | Patron | Wait Staff | Cooking Staff, Head Chef | Cooking Staff
Prepare food | Cooking Staff | Head Chef | Wait Staff | Patron, Bussing Staff
Serve food | Wait Staff, Bussing Staff | Manager | Cooking Staff, Head Chef | Patron
Eat food | Patron | Patron | Wait Staff, Bussing Staff | Cooking Staff, Head Chef
Pay bill | Patron, Cashier | Patron | Wait Staff | Manager, Host, Bussing Staff
Clean table | Bussing Staff | Manager | Wait Staff | Host
RACI v2
SIPOC Process Step | Patron | Host | Wait Staff | Manager | Cooking Staff | Head Chef | Bussing Staff | Cashier
Assign table | Informed | Responsible | Consulted | Accountable |  |  | Informed
Order food | Responsible |  | Accountable, Responsible |  | Informed, Consulted | Informed, Consulted
Prepare food | Informed |  | Consulted |  | Responsible | Accountable, Responsible | Informed
Serve food | Informed |  | Responsible | Accountable | Consulted | Consulted | Responsible
Eat food | Accountable, Responsible |  | Consulted |  | Informed | Informed | Consulted
Pay bill | Accountable, Responsible | Informed | Consulted | Informed |  |  | Informed | Responsible
Clean table |  | Informed | Consulted | Accountable |  |  | Responsible

## Resources
Lean Six Sigma Technique Tips - SIPOC | Pyzdek Institute | https://www.youtube.com/watch?v=AlN7eNOBPzg | 7 minutes
How to complete the SIPOC Diagram | Six Sigma Development Solutions Inc. | https://youtu.be/x8_I19PJBY8 | 1 minute
SIPOC | Wikipedia | https://en.wikipedia.org/wiki/SIPOC
SIPOC | LeanOhio | https://www.youtube.com/watch?v=_2_Ijfg4EVk | 4 minutes
SIPOC Diagram explained (with example) | Bzhwen A Kadir | https://www.youtube.com/watch?v=j9oWnnbtkOo | 7 minutes