## Template
University Libraries Digital Preservation & Access SIPOC Template
High Level Process (Phase 1): | Born Digital Accessioning |  |  | Prepared By:
Suppliers | Inputs | Process |  | Outputs | Customers
Who provides the inputs? | What inputs are provides? | What are the high level process steps? |  | What outputs are provided? | Who recieves a deliverable from the process?
SIPOC (Phase 6) | SIPOC (Phase 5) | SIPOC (Phase 2) |  | SIPOC (Phase 3) | SIPOC (Phase 4) | Notes:
Donor Department | Communication | First Step | Request to transfer electronic records to Archives | Communication with donor or department | Archives staff Donor Department | What is the nature of this Output communication? How has it transformed in this process? Donor or department communicates with Archives; Archives responds with information about what types of material we want/why/parameters/how the process works/etc
Donor Department | Material Description of material | Step 2 | Appraise material | Decision to accept material | Archives staff Donor Department
Donor Department | Material | Step 3 | Transfer material | Materials in Archives' Custody | Archives staff Digital Preservation | Is this step only necessary if it is the tranfer of files on media vs. to Box? Patron/department have to transfer material to us and let us know that the material is there
Archives staff Digitial Preservation | Material and metadata | Step 4 | Accession material | Donor paperwork (Deed of Gift) Accession record/inventory Material and metadata | Donor Archives staff
Archives staff | Material and metadata | Last Step | Store material | Securely stored material and metadata | Shared drives Box DC Stacks | Securely stored (?) Material and metadata (Security depends on where the material is actually stored)

## RACI v1
SIPOC Process Step1 | Responsible | Accountable | Consulted | Informed
Request to transfer electronic records to Archives | OCA head BPCRCAP head Assistant University Archivist | Head of Archives/University Archivist | Digital Preservation Librarian
Appraise material | OCA head BPCRCAP head Assistant University Archivist | Head of Archives/University Archivist | Digital Preservation Librarian
Transfer material (OCA) | Donor | OCA head | Digital Preservation Librarian
Transfer material (BPCRCAP) | Donor | BPCRCAP head | Digital Preservation Librarian
Transfer material (University Archivist) | University Department | Assistant University Archivist | Digital Preservation Librarian
Accession material (OCA & BPCRCAP) | ADA staff | ADA head | OCA head BPCRCAP head | Donor
Accession material (University Archivist) | Assistant University Archivist | University Archivist | OCA head BPCRCAP head | University Department
Store material (OCA & BPCRCAP) | ADA staff | ADA head | OCA head BPCRCAP head | Donor
Store material (University Archivist) | Assistant University Archivist | University Archivist | Digital Preservation Librarian | OCA head BPCRCAP head
1At a minimum, identify the process steps from the SIPOC; but this can be augmented with more granular steps.
ADA = Archival Description & Access
OCA = Ohio Congressional Archives
BPCRCAP = Byrd Polar & Climate Research Center Archival Program

## RACI v2
SIPOC Process Step1 | Internal |  |  |  | External2
| Head of Archives/University Archivist | OCA Head | BPCRCAP Head | Assistant University Archivist | ADA Head | ADA Staff | Digital Preservation Librarian | University Department | Donor
Request to transfer electronic records to Archives | Accountable | Responsible | Responsible | Responsible |  |  | Consulted
Appraise material | Accountable | Responsible | Responsible | Responsible |  |  | Consulted
Transfer material (OCA) |  | Accountable |  |  |  |  | Consulted |  | Responsible
Transfer material (BPCRCAP) |  |  | Accountable |  |  |  | Consulted |  | Responsible
Transfer material (University Archivist) |  | Consulted | Consulted | Accountable |  |  | Consulted | Responsible
Accession material (OCA & BPCRCAP) |  | Consulted | Consulted |  | Accountable | Responsible |  |  | Informed
Accession material (University Archivist) | Accountable |  |  | Responsible |  |  |  | Informed
Store material (OCA & BPCRCAP) |  | Consulted | Consulted |  | Accountable | Responsible |  |  | Informed
Store material (University Archivist) | Accountable | Informed | Informed | Responsible |  |  | Consulted
1At a minimum, identify the process steps from the SIPOC; but this can be augmented with more granular steps.
2"External" to the unit creating the SIPOC (e.g. Metadata Initiatives is "external" to Preservation & Digitization)
3While the template identifies 8 roles, this is neither a minimum nor a maximum, it all depends upon your workflow and processes. Name the roles (and/or individuals) Identify who is: - Responsible - Accountable - Consulted - Informed

## ReadMe
SIPOC | = | Suppliers, Inputs, Process, Outputs and Customers
Suppliers | = | Provider of Inputs to the Process
Inputs | = | Define the material, service and/or information that are used by the process to produce the outputs
Process | = | A defined sequence of activities, usually adds value to Inputs to produce Outputs for the Customers. Transforms Input to Output. Verb>Noun Structure 4 to 7 high level steps
Outputs | = | The products, services, and/or information (transformed Inputs) that are valuable to the Customers
Customers | = | The users of the Outputs produced by the Process.
1Purpose: |  | To give people who are unfamiliar with a process a high-level overview
To reacquaint people whose familiarity with a process has faded or become out-of-date due to process changes
To help people in defining a new process
Support the definition, structuring and scoping of complex processes
Identifying possible problems and/or weaknesses in work processes
What the process IS, not what it should be
1Assumptions: |  | Suppliers and customers may be internal or external to the organization that performs the process.
Inputs and outputs may be materials, services, or information.
The focus is on capturing the set of inputs and outputs rather than the individual steps in the process
2Phases: | 1 | Name the Process
| 2 | Map it in 4 to 7 high level steps:
2a First step
2b Last Step
2c In-between steps
| 3 | Identify the outputs of this process.
| 4 | Identify the customers that will receive the outputs of this process.
| 5 | Identify the inputs required for the process to function properly.
| 6 | Identify the suppliers of the inputs that are required by the process.
| 7 | Discuss with project sponsor, Champion and other involved stakeholders for verification.
3RACI |  | There is a distinction between a role and individually identified people: a role is a descriptor of an associated set of tasks; may be performed by many people; and one person can perform many roles.
| R | Responsible (also Recommender): Those who do the work to complete the task. There is at least one role with a participation type of responsible, although others can be delegated to assist in the work required.
| A | Accountable (also Approver or final approving authority): The one ultimately answerable for the correct and thorough completion of the deliverable or task, the one who ensures the prerequisites of the task are met and who delegates the work to those responsible. In other words, an accountable must sign off (approve) work that responsible provides. There must be only one accountable specified for each task or deliverable.
| C | Consulted (sometimes Consultant or counsel): Those whose opinions are sought, typically subject matter experts; and with whom there is two-way communication.
| I | Informed (also Informee): Those who are kept up-to-date on progress, often only on completion of the task or deliverable; and with whom there is just one-way communication
The RACI can be completed by creating a matrix where the rows are at a minimum the process steps from the SIPOC, but could be augmented with more granular steps.
The RACI can be then be filled out in one of two manners: v1) the columns represent R-A-C-I and for each process the role(s)/person(s) is/are identified. Each step must have someone responsible (can be multiple) and accountable (can only be one); v2) the columns represent the various roles, and for each step one indicates if the role is responsible, accountable, consulted and/or informed.
Notes: | 1 | Adapted from https://en.wikipedia.org/wiki/SIPOC
| 2 | Adapted from https://www.isixsigma.com/tools-templates/sipoc-copis/sipoc-diagram/
| 3 | Adapted from https://en.wikipedia.org/wiki/Responsibility_assignment_matrix

## Example - SIPOC
University Libraries Digital Preservation & Access SIPOC Template
High Level Process (Phase 1): | Restaurant Visit |  |  | Prepared By: | General Manager, Head Waitperson, & Head Chef
Suppliers | Inputs | Process |  | Outputs | Customers
Who provides the inputs? | What inputs are provides? | What are the high level process steps? |  | What outputs are provided? | Who recieves a deliverable from the process?
SIPOC (Phase 6) | SIPOC (Phase 5) | SIPOC (Phase 2) |  | SIPOC (Phase 3) | SIPOC (Phase 4)
Maître d' | Table request | First Step | Assign table | Occupied table | Restaurant guest
Restaurant guest | Verbal order | Step 2 | Order food | Written order | Wait staff Cooking staff
Cooking staff | Various food products | Step 3 | Prepare food | Prepared meal | Wait staff
Wait staff | Prepared food | Step 4 | Serve food | Delivered meal | Restaurant guest
Restaurant guest | Eating | Step 5 | Eat food | Table to be cleared | Bussing staff
Wait staff | Meal invoice | Step 6 | Pay bill | Money transfer Receipt | Restaurant guest Cashier
Bussing Staff | Reset table | Last Step | Clean table | Available table | Maître d'

## Example - RACI
RACI v1
SIPOC Process Step | Responsible | Accountable | Consulted | Informed
Assign table | Host | Manager | Wait Staff | Patron
Order food | Patron | Wait Staff | Cooking Staff, Head Chef | Cooking Staff
Prepare food | Cooking Staff | Head Chef | Wait Staff | Patron, Bussing Staff
Serve food | Wait Staff, Bussing Staff | Manager | Cooking Staff, Head Chef | Patron
Eat food | Patron | Patron | Wait Staff, Bussing Staff | Cooking Staff, Head Chef
Pay bill | Patron, Cashier | Patron | Wait Staff | Manager, Host, Bussing Staff
Clean table | Bussing Staff | Manager | Wait Staff | Host
RACI v2
SIPOC Process Step | Patron | Host | Wait Staff | Manager | Cooking Staff | Head Chef | Bussing Staff | Cashier
Assign table | Informed | Responsible | Consulted | Accountable |  |  | Informed
Order food | Responsible |  | Accountable, Responsible |  | Informed, Consulted | Informed, Consulted
Prepare food | Informed |  | Consulted |  | Responsible | Accountable, Responsible | Informed
Serve food | Informed |  | Responsible | Accountable | Consulted | Consulted | Responsible
Eat food | Accountable, Responsible |  | Consulted |  | Informed | Informed | Consulted
Pay bill | Accountable, Responsible | Informed | Consulted | Informed |  |  | Informed | Responsible
Clean table |  | Informed | Consulted | Accountable |  |  | Responsible

## Resources
Lean Six Sigma Technique Tips - SIPOC | Pyzdek Institute | https://www.youtube.com/watch?v=AlN7eNOBPzg | 7 minutes
How to complete the SIPOC Diagram | Six Sigma Development Solutions Inc. | https://youtu.be/x8_I19PJBY8 | 1 minute
SIPOC | Wikipedia | https://en.wikipedia.org/wiki/SIPOC
SIPOC | LeanOhio | https://www.youtube.com/watch?v=_2_Ijfg4EVk | 4 minutes
SIPOC Diagram explained (with example) | Bzhwen A Kadir | https://www.youtube.com/watch?v=j9oWnnbtkOo | 7 minutes