## Slide 1: Web Redesign Project Overview
Robyn Ness, Project Lead
2/28/2017

## Slide 2: Project Goals
Redesign library.osu.edu in a way that is easy for users to navigate.
  Apply user-centered design and iterative development to achieve this.
  Communicate openly about decision making and progress.

## Slide 3: Project Team
Sponsors: Jennifer Vinopal & Lisa Carter
Project Lead: Robyn Ness
Implementation Lead: Beth Snapp
Web Environment: AD&S + Infrastructure Support
User Experience (UX): Meris Mandernach + others
Drupal User Training: Sue Beck
Functional Experts: many of you

## Slide 4: Milestones
Content analysis of current website (WI 2017)
OSUL functionality discussions (WI 2017, iterative)
User needs surveys (WI 2017, iterative)
Form a user experience (UX) cohort; start user testing (WI/SP 2017, testing iterative)
Initial draft of information architecture (SP 2017, rework based on testing)
Drupal training and content migration (late-SP 2017, ongoing)
Release early preview site for public feedback (mid-SU 2017)
Replace old site with new site (as soon as January 1, 2018, depending on content readiness and user testing results)

## Slide 5: Some FAQs

## Slide 6: Q: When will staff be able to "see something"?
OSUL will be able to see a rough version of the site in late spring 2017, when content training and content migration is scheduled to begin.
A public preview will be offered mid-summer 2017. This preview will not be a complete site, but it will include testable portions for our users to try.

## Slide 7: Q: Won’t it be difficult to migrate content if the site isn’t complete?
Our new content management system, (Drupal) is modern, modular, and highly configurable. We can begin moving content over the summer, even when we aren’t sure yet which labels or sections it will appear under in the finished site.
  However, be prepared to revise some of your content for the new site’s format. We hope to hire a content person to assist.

## Slide 8: Q: The site switchover is not going to happen in the middle of a semester, is it?
Absolutely not! But, if the new site is relatively complete based on content readiness and user testing, we may release it in parallel with the old site.

## Slide 9: Q: What kinds of user testing will we use to get feedback?
Surveys with structured and open-ended questions - to ask our users about their priorities and opinions
Face-to-face methods, such as cardsorting and focus groups - to explore user-focused terminology and intuitive information architecture
Task-based user testing - to test portions of the site for ease of use
Web analytics and heat mapping - to look for use patterns indicative of good or bad design

## Slide 10: Related Info: The UX Cohort
Implements user research for both the Website Redesign Project and the Discovery Project.
Anyone with an interest in improving user experience can join.
Robyn Ness and Meris Mandernach are co-leads.
    More information coming soon...

## Slide 11: Managers, We Need Your Help
Participate in OSUL functionality discussions
  More information coming very soon
Share project information with your teams
Recommend participants from among your users for face-to-face groups and user testing
Encourage interested members of your staff to join the User Experience (UX) Cohort
  More information coming soon

## Slide 12: Just in Case…

## Slide 13
User Testing and Research Plan
Step 1: Research and Discovery
Step 2: Site Structure/Content
Step 3: Visual Design
Step 4: Site Development
Purpose:
Define user needs and priorities
Method: Survey
Participants: Split across undergrad, graduate student, and faculty; test with 6-8 circ/public services staff
Questions: Ask users to choose/rank tasks important to them or not important to them; free-form field for what they most want to be able to do or what they can’t do easily now
Method: Functional Expertise (Iterative)
Participants: Content and service owners
Goal: 1) Define personas to capture uniqueness of each audience. 2) Identify site functional needs.
Purpose:
Explore content relationships and user-focused language and labeling
Create sitemap
Test navigation structures and labeling
Method: Cardsort
Participants: 3-4 undergrads, 3-4 graduate students/instructors; test with 3 library staff, at least one a student
Method: Survey (Iterative)
Participants: Split across undergrad, graduate student, and faculty per round; initial test with 6-8 library staff
Questions: Ask participants to compare two or more navigation categories; select 3-5 priority tasks and ask “Where would you click to find _____?”
Purpose:
Finalize page “footprint”
Test visual designs
Confirm navigation structures and labeling
Method: Survey
Participants: Split across undergrad, graduate student, and faculty; test with 6-8 library staff
Questions: Ask participants to compare two or more designs and state preference; select 3-5 priority tasks and ask “where would you click to find _____?”
Purpose:
Test interaction and flow; including deeper paths
Confirm effectiveness of visual design and visual hierarchy
Method: User Testing / Think Aloud (Iterative)
Participants: 2-3 undergrads, 2-3 graduate students/instructors per round; initial test with 3 library staff, at least one a student
Tasks: Select 3-5 priority tasks, including multi-step tasks, such as find hours, log into your account, locate online journals, find your subject librarian, find a study space, etc.
Existing Data Review
User Priorities
Survey
Content Cluster
and Labeling Cardsorts
Wireframe
Surveys
Visual Design
Survey
Task-Based
User Testing
iterative
iterative
Date: 2/20/2017
Functional
Expert Mtgs
iterative

## Slide 14
MARCH
FEBRUARY
FINALS
APRIL
SPRING BREAK
production env / visual elements
prototyping / proof of concept / testing modules
MAY
user input*
site dev
qa & review
content
visual design
END USER POOL*
WEB REDESIGN TIMELINE – PART 1 – DRAFT
vis design testing
sitemap survey
card sort task
user priorities surv
existing data
content revision
wireframe nav / refinement
info arch draft
funct. expert mtgs/ requirements
iterative
Step 1: Research and Discovery
Step 2: Site Structure/Content
Step 3: Visual Design
Step 4: Site Development
Step 5: Testing & Review
Web Redesign Project Plan Steps
refinement / customization
vis. design
iterative
iterative
vis des requirements
clarify internal goals
sitemap
review
content list & user survey results
wireframe nav &
visual design preview
sponsor approval
kick-off
site map; form user testing group
begin functional requirements mtgs
share wireframe
visual design preview;
begin Drupal training
all-lib updates
visual design survey results
COLOR KEY:
COMMUNICATION:
NOTES:
End User Pool – Traditionally, it’s harder to get users’ attention leading into finals. We should plan to wait until fall for most testing after this point.
User Input – Surveys and face-to-face testing will be piloted with OSUL staff, and their data will be considered, although not combined, with other user input.
Date: 2/21/2017
iterative

## Slide 15
SEPTEMBER
SUMMER
JANUARY
OCTOBER
production env / refining visual elements and structural design
DECEMBER
user input*
site dev
qa & review
content
visual design
END USER POOL*
WEB REDESIGN TIMELINE – PART 2 - DRAFT
content revision
refinement / customization
iterative
content progress (repeating)
sponsor approval
all-lib updates
COMMUNICATION:
NOVEMBER
task-based testing
iterative
user testing progress (repeating)
final site review; go/no go decision
NOTES:
Time dividers not equally spaced: Summer (May – August) has been condensed for space.
End User Pool – Traditionally, it’s harder to get users’ attention leading into finals. We should plan to complete user testing before Thanksgiving break.
User Input – Surveys and face-to-face testing will be piloted with OSUL staff, and their data will be considered, although not combined, with other user input.
LAUNCH implies a public swap of new for old site; a preview site release is planned for mid-summer.
content work
plan for instructional
changes if launch in Dec.
announcement of launch date, final review for swap with old site
targeted testing
wide-scale testing
LAUNCH?*
release preview;
invite to review/
QA test
approve release of preview site
Date: 2/21/2017
PUBLIC PREVIEW